## Slide 1: Proposed Timeline for RD CS for FY2 Programme
R-3months (+)
FY2 Rotation End
Publicise about programme to potential Registrars & ask them to book onto CS course
R-2 months
Inform FY2s Opt in vs Opt out approach
R-6 weeks
Finalise RD CS details with Registrars and begin matching process
R-2 weeks
Finalise and publicise match!
R (close to)
Start of rotation CS meeting
RDCS & FY2. dCS present initially
FY2 Rotation (R) Start
R+2 weeks
Check in meeting RD CS and dCS
R+8 weeks
RD CS & FY2 Midpoint meeting
&
RD CS & dCS mentoring meeting
R+15 weeks
RD CS & dCS final mentoring meeting including discussing end of placement reports
R+16 weeks
RD CS & FY2 final meeting
Post supervision evaluation
Mr Hugo Cohen, Faculty & Education Fellow, Dr Jane Thurlow, Associate Dean Professional Education and Development. NHS England Southwest